## Sheet1
User Story	Story Description (Card)	Volunteer	Task Details	Initial Effort Estimate (hrs)	New Estimates of Effort remaining at end of					Status
					Day1	Day2	Day3	Day4	Day5
US001	As a customer-account executive /cashier / teller / I want to be able to log in the bank website with my user ID and password / So that I carry out my transactions	Elza	Write a program	3	2	2	0	0	0	Closed
		Elza	Design the UI for the Home page	1.5	1	0.5	0	0	0	Closed
		Elza	Design and create the DB fields	1	0.5	0.5	0	0	0	Closed
		Elza	Write test conditions	2	2	2	2	0	0	Closed
		Elza	validation	1.5	2	2	0	0	0	Closed

US002	As a customer-account executive / I want to be able to capture new customer information / So that I can create a new customer in the system	Elza	Write a program	3.5	0	0	0	0	0	Closed
		Deepika	Design the UI for the Home page	1.5	1	0.5	0	0	0	Closed
		Balaraju	Design and create the DB fields	1	0	0	0	0	0	Closed
		sumana	Write test conditions	2	2	2	2	1	0	Closed
		Abhijit	validation	2	0	0	0	0	0	Closed
		sravani	Test cases and Factory pattern	3.5	0	0	0	0	0	Closed

US003	As a customer-account executive / I want to be able to edit existing customer information / So that I can store the updated customer information in the system	Sravani	Write a program	3	2	1	0	0	0	Closed
		Shankar	Design the UI for the Home page	1.5	0.5	0	0	0	0	Closed
		Balaraju	Design and create the DB fields	1	0	0	0	0	0	Closed
		elza	Write test conditions	2	1	0	0	0	0	Closed
		Abhijit	validation	2	1	0	0	0	0	Closed
		Sumana	Test cases and Factory pattern	1	0	0	0	0	0	Closed

US004	As a customer-account executive / I want to be able to delete existing customer from system	Sumana	Write a program	3.5	2	1	1	0	0	Closed
		deepika	Design the UI for the Home page	2	1	0	0	0	0	Closed
		balaraju	Design and create the DB fields	1	0	0	0	0	0	Closed
		abhijit	Write test conditions	3	2	1.5	1.5	1.5	0	Closed
		sravani	validation	3	3	2	0	0	0	Closed

US005	As a customer-account executive / I want to be able to view the status of all the customers of the bank	Deepika	Write a program	3.5	1.5	0	0	0	0	Closed
		balaraju	Design the UI for the Home page	1.5	1.5	1.5	0	0	0	Closed
		elza	Design and create the DB fields	1	0	0	0	0	0	Closed
		sravani	Write test conditions	2	1	0	0	0	0	Closed
		abhijit	validation	2	2	2	1	0	0	Closed

US006	As a customer-account executive / I want to be able to capture account details / So that I can create a new bank account for an existing customer	Abhijit	Account details display to do transaction	4	0	2	2	0	0	Closed
		deepika	Write a program	3.5	1.5	0	0	0	0	Closed
		elza	Design the UI for the Home page	1.5	1.5	1.5	0	0	0	Closed
		sravani	Design and create the DB fields	1	0	0	0	0	0	Closed
		Balaraju	Write test conditions	2	1	0	0	0	0	Closed
		sumana	validation	2	2	2	1	0	0	Closed

US007	As a customer-account executive / I want to be able to delete an account of an existing customer	Balaraju	Write a program	3	1	0	0	0	0	Closed
		deepika	Design the UI for the Home page	1.5	1	0	0	0	0	Closed
		abhijit	Design and create the DB fields	0.5	0	0	0	0	0	Closed
		shankar	Write test conditions	3	3	2	1	1	0	Closed
		sravani	validation	3	3	2	1	1	0	Closed

US008	As a customer-account executive / I want to be able to view the status of all the accounts of the bank	Deepika	Write a program	4	2	0	0	0	0	Closed
		sravani	Design the UI for the Home page	2	0.5	0	0	0	0	Closed
		balaraju	Design and create the DB fields	0.5	0	0	0	0	0	Closed
		shankar	Write test conditions	3	2	2	0	0	0	Closed
		abhijit	validation	2	2	2	0	0	0	Closed

US009	As a customer-account executive / I want to be able to search for a customer / So that I am able to view the details	Sravani	Write a program	4	2	0	0	0	0	Closed
		deepika	Design the UI for the Home page	2	2	2	0	0	0	Closed
		balaraju	Design and create the DB fields	0.5	0	0	0	0	0	Closed
		sumana	Write test conditions	3	3	2.5	2.5	2.5	0	Closed
		elza	validation	2	2	0	0	0	0	Closed

US010	As a Cashier/ Teller / I want to be able to search for a bank account / So that I am able to view the details	Sravani	Create DAO and servlet	2	0	0	0	0	0	Closed
		balaraju	JSP Pages	3	1.5	1.5	1.5	0	0	Closed
		deepika	JSP Styling	0.5	0	0	0	0	0	Closed
		abhijit	Validations	3	3	3	1.5	1.5	0	Closed
		sumana	Test cases and Factory pattern	2	2	2	1.5	1.5	0	Closed

US011	As a Cashier/ Teller / I want to be able to deposit money into a customer's account / So that I am able to service the customer's request	Sumana	Create DAO and servlet	4	2	0	0	0	0	Closed
		balaraju	JSP Pages	2	2	2	0	0	0	Closed
		deepika	JSP Styling	1	1	1	1	0	0	Closed
		abhijit	Exceptions	3	3	3	1.5	1.5	0	Closed
		sravani	Validations	2	2	2	1	1	0	Closed
		elza	Test cases and Factory pattern	1	0	0	1	0	0	Closed

US012	As a Cashier/ Teller / I want to be able to withdraw money from a customer's account / So that I am able to service the customer's request	Shankar	Create DAO and servlet	4	3	2	2	2	0	Closed
		sravani	JSP Pages	2	2	2	1	1	0	Closed
		deepika	JSP Styling	0.5	0	0	0	0	0	Closed
		abhijit	Exceptions	3	3	1	1	1	0	Closed
		balaraju	Validations	2	2	2	0	0	0	Closed
		sumana	Test cases and Factory pattern	1	0	0	1	0	0	Closed

US013	As a Cashier/ Teller / I want to be able to transfer money from a customer's account / So that I am able to service the customer's request	Sravani	Create DAO and servlet	2	2	0	0	0	0	Closed
		balaraju	JSP Pages	2	2	2	2	2	0	Closed
		deepika	JSP Styling	0.5	0	0	0	0	0	Closed
		elza	Validations	3	3	3	3	3	0	Closed
		sumana	Test cases and Factory pattern	3	3	3	3	3	0	Closed

US014	As a Cashier/ Teller / I want to be able to print an account statement / So that I am able to service the customer's request	Abhijit	Create DAO and servlet	5	3	1	1	0	0	Closed
		balaraju	JSP Pages	2.5	0.5	0	0	0	0	Closed
		deepika	JSP Styling	2	2	0	0	0	0	Closed
		elza	Validations	1.5	0.5	0	0	0	0	Closed
		sravani	Test cases and Factory pattern	1.5	1	0	0	0		Closed

Logger implementation
	task1	sravani	study the logger part	9	4.5	4.5	0	0	0	Closed
	rask2	sravani	implement the logger part	9	9	9	4.5	2	0	Closed

factory set implementation
	Task 1	elza	factory study and implementation	10	6.5	4	2	0	0	Closed
	Task 2	sravani	factory study and implementation	10	7	4	2	0	0	Closed

Exceptional Handling
	Task 1	sumana	study the exceptional handling	8	4	2	0	0	0	Closed
	Task 2	sumana	implement the exceptional handling	8	8	8	8	4	0	Closed

Rechecking validations and improvisations
	Task 1	abhijit	check every boxes	8	8	6	4	2	0	Closed
	Task 2	abhijit	make other validations to work	8	8	6	4	2	0	Closed

debugging

	Task 1	all members	debugg every part and correct the things to work perfect	20	10.5	10.5	5.5	5	0	Closed

			Total	252.5	167.5	120	68	34.5	0	Closed

## Sheet2
Total	252.5	167.5	120	68	34.5	0	Closed